## Project_data(synthetic)
ID | Activity | Duration (Weeks) | Start Date | End Date | Depends On | Progress
1 | SOR & RFQ Preparation | 3 | 2026-08-01 | 2026-08-22 |  | Completed
2 | CAN DBC Finalized & Freezed | 2 | 2026-09-06 | 2026-09-20 | 1 | Completed
3 | Application Vehicle Availability | 3 | 2026-09-29 | 2026-10-20 | 2 | Completed
4 | ABS SOA SW to Application Engineer | 4 | 2026-10-21 | 2026-11-18 | 3 | Completed
5 | Vehicle Readiness Check as per Checklist | 2 | 2026-11-19 | 2026-12-03 | 4 | Completed
6 | ABS Instrumentation & Static Calibration | 2 | 2026-12-12 | 2026-12-26 | 5 | Completed
7 | ABS Dynamic Calibration (3 Mode) | 3 | 2026-12-27 | 2027-01-17 | 6 | Completed
8 | Offer Drawing Release to TVS | 1 | 2027-01-18 | 2027-01-25 | 7 | In Progress
9 | ABS Joint Test | 2 | 2027-01-26 | 2027-02-09 | 8 | Not Started
11 | ABS JT Sign-off | 1 | 2027-02-23 | 2027-03-02 | 10 | Not Started
12 | Offer Drawing Approval from TVSM | 2 | 2027-03-03 | 2027-03-17 | 11 | Not Started
14 | Test SW Release to Bosch Application Engineer | 1 | 2027-03-26 | 2027-04-02 | 13 | Not Started
15 | Vehicle Level Verification (Cat.3/5 Validation) | 3 | 2027-04-03 | 2027-04-24 | 14 | Not Started
16 | Homologation SW Delivery to TVS | 2 | 2027-04-25 | 2027-05-09 | 15 | Not Started
17 | VTC/EV SW Release to Bosch Application Engineer | 1 | 2027-05-02 | 2027-05-09 |  | Not Started
18 | Vehicle Level Verification (Cat.3/5 Validation) | 2 | 2027-05-10 | 2027-05-24 | 17 | Not Started
19 | Series SW Release to Bosch Plant (RT8) | 2 | 2027-05-25 | 2027-06-08 | 18 | Not Started
20 | BOM Preparation & Release to ChkP | 2 | 2027-06-09 | 2027-06-23 | 19 | Not Started
21 | Plant Readiness & Part Delivery | 3 | 2027-06-24 | 2027-07-15 | 20 | Not Started
22 | PPAP Delivery | 2 | 2027-08-02 | 2027-08-16 | 21 | Not Started